## Sheet1
Weekly Work Plan
Date of the duration | 2026-05-20 ~ 2026-05-22
Project Name | TMED-II Phase III - Motor Line
Construction company | Proyectos BODE (Borbolla Automation Inc.)
Manager of project | Luis Borbolla
Manager Transys | JaeWook Bae
Department in charge | Facilities / Maintenance
Activities place (AREA) | Motor Line Area
Date | Working Time | Manager | People Required | Activities | Height Works | Cut and Welding | Heavy Equipment | Etcetera | Remarks
2026-05-20 | 08:00-18:00 | Luis Borbolla | 5 | Motor Line marking layout on floor. - Scale verification (column spacing vs DWG) - Datum column identification (A1) - Machine footprint marking using chalk line + spray paint - Reference: V38 motor line marking layout DWG | No | No | No | Tape measures (2x 50m), chalk line, spray paint, laser distance meter | Client DWG provided. Scale verification mandatory before marking.
2026-05-21 | 08:00-18:00 | Luis Borbolla | 5 | Motor Line marking layout completion. - Continue machine footprint marking - Verify all 53 process stations marked - Column grid reference lines - Final dimension verification vs DWG | No | No | No | Same as Day 1 | Must complete before container arrival.
2026-05-22 | 07:00-18:00 | Luis Borbolla | 5 | Line marking completion + 11 container unloading in-situ. - Finish remaining line marking - Receive 11 containers (Motor Line equipment) - Forklift unloading to marked positions - Verify equipment vs packing list - Photo documentation of each container | No | No | Yes - Forklift(s) | Forklift (2x), pallet jack, packing lists, camera | 11 containers. ~10 containers/day capacity with 2 forklifts. Flat rack containers = forklift only, no crane.